Mayo/Trapollo Touchpoint

9am | January 5, 2022

Location:

|  |  |
| --- | --- |
| Topic | Proponents |
| **Trapollo Agenda Items\***  **Resideo Program Transition updates, timelines and action Items**   * Mayo is delaying the COVID transition at least a few weeks (maybe 2/1) * Delaying direct distribution beyond the COVID overnight shipping transition * Working on maps to build programs/conditions in Biofourmis going into Q2 or Q3 2022 * Consider: inventory shipping * Consider: inventory disposal * Consider: anything relative to Resideo (turning off tablets) * Possibility we will attempt to transition and it does not go smoothly- what are the options for rapidly transitioning back to Trapollo?   + Trapollo will maintain inventory and pre-paired kits (pallets of kits ready to go)   + Not much would change with current processes, but API considerations (want to do full testing)   + Could store excess inventory if needed locally to move over quickly   + Trapollo will inform team of possibility to resume relationship with Mayo on COVID/others   + Mayo would like to maintain Trapollo inventory   **API project updates**   * As of last week, Mayo would like to continue project. Trapollo agrees. * Completed and put into production. We will still have the OB COVID ICP with Trapollo and potential future collaboration. * Potential to use API for programs not yet transitioned to Biofourmis. * Targeting interphase to go-live in early March.   **Current and in process TMC Change requests (see end of agenda)** | Trapollo Team |
| File Upload for OB COVID Updates   * Steve sent over a change order for approval in mid-December * Mayo review and provide eSignature | Steve |
| Equipment at Trapollo  Equipment Pending UPS Pick up-224 pending UPS pick up as of ¼   * Many of these are UPS delays currently (weather, holidays, etc) * Nothing looks concerning at this time, still 4-5 days   Trends with getting equipment back | Erin/Ben |
| **Equipment Shipped to Biofourmis**   * Hold at this time * Supply Chain contact- Andres C. | Ben |
| **OB COVID Re-Enrollments**  Scenario 1- Patient still has equipment – no action needed they can start testing again  Scenario 2- Patient needs new equipment - What process should our DOS team follow? Find the member in TMC and create a ticket.   * File Upload will not re-create patient, but patient may still need equipment * Should File Upload let us know there’s an error and ask if we should ship another kit? Sara reply to Steve’s e-mail with Mayo’s preferred solution to determine feasibility. * API situation- what would we want to happen? | Sara |
| **Arizona ED Inventory**  Sara will send e-mail with details  More kits need to be shipped to Arizona today for delivery by the weekend | Sara |
| Review Issue Tracker\* | Add member name |
| Change Requests in Progress/Upcoming\* |  |
| Daily Updates and Issue Resolutions: [remotemonope@mayo.edu](mailto:remotemonope@mayo.edu) |  |

Outages: [DLCDHRPMTECHTEAM@mayo.edu](mailto:DLCDHRPMTECHTEAM@mayo.edu)